## GANTT CHART 2
PROJECT NAME | NEXUS
START DATE | 2024-10-01
 | time axis 2024-10-01 to 2024-11-26
Task | Subtask | Responsible | Duration (days) | Start Date | End Date | Status
Requirement Gathering | Stakeholder Interviews | Alice Johnson | 5 | 2024-10-01 | 2024-10-08 | Completed | bar: 2024-10-01 to 2024-10-08
| Document Requirements | Alice Johnson | 5 | 2024-10-03 | 2024-10-10 | Completed | bar: 2024-10-03 to 2024-10-10
| Review Requirements | Alice Johnson | 7 | 2024-10-05 | 2024-10-15 | InProgress | bar: 2024-10-05 to 2024-10-15
Design Architecture | Create High-Level Design | Bob Smith | 3 | 2024-10-06 | 2024-10-09 | InProgress | bar: 2024-10-06 to 2024-10-09
| Create Detailed Design | Bob Smith | 3 | 2024-10-09 | 2024-10-14 | Recommit | bar: 2024-10-09 to 2024-10-14
| Design Review | Bob Smith | 1 | 2024-10-12 | 2024-10-14 | Recommit | bar: 2024-10-12 to 2024-10-14
Database Setup | Define Schema | Charlie Brown | 2 | 2024-10-13 | 2024-10-15 | InProgress | bar: 2024-10-13 to 2024-10-15
| Set Up Database | Charlie Brown | 2 | 2024-10-15 | 2024-10-17 | InProgress | bar: 2024-10-15 to 2024-10-17
| Populate Initial Data | Charlie Brown | 1 | 2024-10-17 | 2024-10-18 | InProgress | bar: 2024-10-17 to 2024-10-18
Frontend Development | UI Design | Dana White | 5 | 2024-10-18 | 2024-10-25 | Completed | bar: 2024-10-18 to 2024-10-25
| Implement UI Components | Dana White | 8 | 2024-10-23 | 2024-11-04 | Completed | bar: 2024-10-23 to 2024-11-04
| Frontend Testing | Dana White | 3 | 2024-10-31 | 2024-11-05 | Completed | bar: 2024-10-31 to 2024-11-05
Backend Development | API Design | Ethan Green | 5 | 2024-10-18 | 2024-10-25 | Completed | bar: 2024-10-18 to 2024-10-25
| Implement APIs | Ethan Green | 8 | 2024-10-23 | 2024-11-04 | Recommit | bar: 2024-10-23 to 2024-11-04
| Backend Testing | Ethan Green | 3 | 2024-10-31 | 2024-11-05 | Recommit | bar: 2024-10-31 to 2024-11-05
Testing | Create Test Cases | Fiona Black | 3 | 2024-11-03 | 2024-11-06 | Recommit | bar: 2024-11-03 to 2024-11-06
| Execute Test Cases | Fiona Black | 3 | 2024-11-06 | 2024-11-11 | Recommit | bar: 2024-11-06 to 2024-11-11
| Bug Reporting | Fiona Black | 2 | 2024-11-09 | 2024-11-12 | Recommit | bar: 2024-11-09 to 2024-11-12
Deployment | Prepare Deployment Plan | George Blue | 1 | 2024-11-11 | 2024-11-12 | InProgress | bar: 2024-11-11 to 2024-11-12
| Execute Deployment | George Blue | 2 | 2024-11-12 | 2024-11-14 | InProgress | bar: 2024-11-12 to 2024-11-14
| Verify Deployment | George Blue | 2 | 2024-11-14 | 2024-11-18 | InProgress | bar: 2024-11-14 to 2024-11-18
User Training | Develop Training Materials | Hannah Red | 3 | 2024-11-16 | 2024-11-20 | Completed | bar: 2024-11-16 to 2024-11-20
| Conduct Training Sessions | Hannah Red | 2 | 2024-11-19 | 2024-11-21 | Completed | bar: 2024-11-19 to 2024-11-21
Project Review | Gather Feedback | Ian Grey | 3 | 2024-11-21 | 2024-11-26 | Recommit | bar: 2024-11-21 to 2024-11-26
| Finalize Project Report | Ian Grey | 2 | 2024-11-24 | 2024-11-26 | Recommit | bar: 2024-11-24 to 2024-11-26
Formulas:
End Date = WORKDAY([Start Date],[Duration (days)])

## GANTT CHART 3
[8 empty] | 45566 | 45622
PROJECT NAME | NEXUS
START DATE | 2024-10-01
Task | Subtask | Responsible | Duration (days) | Start Date | End Date | Days Completed | STATUS
Requirement Gathering | Stakeholder Interviews | Alice Johnson | 5 | 2024-10-01 | 2024-10-08 | 5 | 100%
| Document Requirements | Alice Johnson | 5 | 2024-10-03 | 2024-10-10 | 5 | 100%
| Review Requirements | Alice Johnson | 7 | 2024-10-05 | 2024-10-15 | 5 | 71.43%
Design Architecture | Create High-Level Design | Bob Smith | 3 | 2024-10-06 | 2024-10-09 | 2 | 66.67%
| Create Detailed Design | Bob Smith | 3 | 2024-10-09 | 2024-10-14 | 0.3 | 10%
| Design Review | Bob Smith | 1 | 2024-10-12 | 2024-10-14 | 0.05 | 5%
Database Setup | Define Schema | Charlie Brown | 2 | 2024-10-13 | 2024-10-15 | 0.6 | 30%
| Set Up Database | Charlie Brown | 2 | 2024-10-15 | 2024-10-17 | 1.3 | 65%
| Populate Initial Data | Charlie Brown | 1 | 2024-10-17 | 2024-10-18 | 0.55 | 55%
Frontend Development | UI Design | Dana White | 5 | 2024-10-18 | 2024-10-25 | 1.25 | 25%
| Implement UI Components | Dana White | 8 | 2024-10-23 | 2024-11-04 | 7.84 | 98%
| Frontend Testing | Dana White | 3 | 2024-10-31 | 2024-11-05 | 0.72 | 24%
Backend Development | API Design | Ethan Green | 5 | 2024-10-18 | 2024-10-25 | 2.7 | 54%
| Implement APIs | Ethan Green | 8 | 2024-10-23 | 2024-11-04 | 2.72 | 34%
| Backend Testing | Ethan Green | 3 | 2024-10-31 | 2024-11-05 | 1.95 | 65%
Testing | Create Test Cases | Fiona Black | 3 | 2024-11-03 | 2024-11-06 | 1.23 | 41%
| Execute Test Cases | Fiona Black | 3 | 2024-11-06 | 2024-11-11 | 1.71 | 57%
| Bug Reporting | Fiona Black | 2 | 2024-11-09 | 2024-11-12 | 1.56 | 78%
Deployment | Prepare Deployment Plan | George Blue | 1 | 2024-11-11 | 2024-11-12 | 0.61 | 61%
| Execute Deployment | George Blue | 2 | 2024-11-12 | 2024-11-14 | 0.32 | 16%
| Verify Deployment | George Blue | 2 | 2024-11-14 | 2024-11-18 | 1.64 | 82%
User Training | Develop Training Materials | Hannah Red | 3 | 2024-11-16 | 2024-11-20 | 2.16 | 72%
| Conduct Training Sessions | Hannah Red | 2 | 2024-11-19 | 2024-11-21 | 0.54 | 27%
Project Review | Gather Feedback | Ian Grey | 3 | 2024-11-21 | 2024-11-26 | 2.49 | 83%
| Finalize Project Report | Ian Grey | 2 | 2024-11-24 | 2024-11-26 | 1.24 | 62%
Formulas:
End Date = WORKDAY([Start Date],[Duration (days)])